## Implementation Plan
Task | ETA
Day 1: Statistical Tests Foundation | 8 hours
- Create StatisticalTestsCalculator class in backend/validation/statistical_tests.py | 1 hour
- Implement KS (Kolmogorov-Smirnov) test with interpretation | 1 hour
- Implement Gini coefficient calculation with comparison logic | 1 hour
- Add unit tests for KS and Gini functions | 1 hour
- Implement PSI (Population Stability Index) with binning and interpretation | 1.5 hours
- Implement CSI (Characteristic Stability Index) for feature-level stability | 1.5 hours
- Add comprehensive test coverage for PSI and CSI | 1 hour
Day 2: Enhanced Performance Validator | 8 hours
- Enhance PerformanceValidator class with confusion matrix | 1 hour
- Add accuracy, precision, recall, F1 score calculations | 1 hour
- Implement AUC-ROC calculation and classification report | 1 hour
- Integrate statistical tests (KS, Gini) into performance results | 1 hour
- Add performance comparison logic (train vs test vs OOT) | 1 hour
- Create ModelSpecificValidator class in backend/validation/model_specific_validator.py | 1 hour
- Implement Application Scorecard validation (score distribution, rank ordering) | 1 hour
- Implement Behavioral Scorecard validation (time-series stability, lifecycle analysis) | 1 hour
- Implement Collections validation (roll rates, recovery rates, LGD) | 1 hour
Day 3: Enhanced Stability Validator & Compliance | 8 hours
- Enhance StabilityValidator class with PSI/CSI integration | 1 hour
- Add temporal stability analysis and drift detection logic | 1 hour
- Create stability visualization data (PSI trends, feature heatmap) | 1 hour
- Add drift detection for data, concept, and prediction drift | 1 hour
- Create SR117ComplianceChecker class in backend/validation/compliance_checker.py | 1.5 hours
- Define SR 11-7 requirements checklist and validation logic | 1 hour
- Implement compliance scoring and gap analysis | 1 hour
- Generate structured compliance reports with recommendations | 0.5 hours
Day 4: Document Upload & Processing | 8 hours
- Add document upload endpoint /api/upload-documents to backend/main.py | 1 hour
- Implement file validation and storage for PDF, DOCX, CSV | 1 hour
- Implement PDF text extraction using PyMuPDF | 1 hour
- Implement DOCX text extraction using python-docx | 1 hour
- Add document metadata tracking (type, timestamp, size, format) | 1 hour
- Create DocumentAnalyzer class in backend/validation/document_analyzer.py | 1.5 hours
- Implement model information extraction from documents | 1 hour
- Implement SR 11-7 section detection and gap analysis | 1 hour
- Add watsonx.ai integration for document understanding and insights | 0.5 hours
Day 5: Audit Trail & Model Cards | 8 hours
- Create AuditTrailManager class in backend/validation/audit_trail.py | 1.5 hours
- Define audit event structure and implement event logging | 1 hour
- Implement JSON-based storage with timestamp and user tracking | 1 hour
- Add audit logging to all validators (validation start/end, test executions) | 1.5 hours
- Create audit trail API endpoints (/api/audit-trail with filtering) | 1 hour
- Create ModelCardGenerator class in backend/validation/model_card_generator.py | 1 hour
- Define model card template with all required sections | 1 hour
- Implement card generation with auto-population from validation results | 1 hour
- Add PDF and JSON export functionality for model cards | 0.5 hours
Day 6: Enhanced Frontend | 8 hours
- Create DocumentUpload component in frontend/src/components/DocumentUpload.jsx | 1 hour
- Implement drag-and-drop file upload with multiple file support | 1 hour
- Add file type validation, upload progress, and preview | 1 hour
- Add document management UI (list, metadata, delete/replace) | 1 hour
- Integrate document upload with backend API and error handling | 1 hour
- Enhance ValidationResults component with statistical tests display | 1.5 hours
- Add KS, Gini, PSI/CSI visualizations and charts | 1 hour
- Add compliance dashboard with SR 11-7 score and gap analysis | 1 hour
- Add audit trail viewer with timeline and event details | 0.5 hours
Day 7: Integration, Testing & Documentation | 8 hours
- Update ValidationOrchestratorAgent to integrate all new validators | 1 hour
- Wire up statistical tests, model-specific validators, and compliance checker | 1 hour
- End-to-end testing: complete validation flow with all model types | 2 hours
- Test document upload, validation, report generation, audit trail | 1 hour
- Bug fixes, error handling improvements, and performance optimization | 1 hour
- Update API documentation with new endpoints and examples | 1 hour
- Create user guide for document upload, validation, and compliance reporting | 1.5 hours
- Update deployment documentation and final production deployment | 0.5 hours