## Implementation Plan
Task | ETA
Day 1: Statistical Tests Foundation | 8 hours
- Create StatisticalTestsCalculator class in backend/validation/statistical_tests.py | 1 hour
- Implement KS (Kolmogorov-Smirnov) test with interpretation | 1 hour
- Implement Gini coefficient calculation with comparison logic | 1 hour
- Add unit tests for KS and Gini functions | 1 hour
- Implement PSI (Population Stability Index) with binning and interpretation | 1.5 hours
- Implement CSI (Characteristic Stability Index) for feature-level stability | 1.5 hours
- Add comprehensive test coverage for PSI and CSI | 1 hour
Day 2: Enhanced Performance Validator | 8 hours
- Enhance PerformanceValidator class with confusion matrix | 1 hour
- Add accuracy, precision, recall, F1 score calculations | 1 hour
- Implement AUC-ROC calculation and classification report | 1 hour
- Integrate statistical tests (KS, Gini) into performance results | 1 hour
- Add performance comparison logic (train vs test vs OOT) | 1 hour
- Create ModelSpecificValidator class in backend/validation/model_specific_validator.py | 1 hour
- Implement Application Scorecard validation (score distribution, rank ordering) | 1 hour
- Implement Behavioral Scorecard validation (time-series stability, lifecycle analysis) | 1 hour
- Implement Collections validation (roll rates, recovery rates, LGD) | 1 hour
Day 3: Enhanced Stability & Compliance Checker | 8 hours
- Enhance StabilityValidator class with PSI/CSI integration | 1.5 hours
- Add basic stability analysis between train/test/OOT datasets | 1.5 hours
- Create SR117ComplianceChecker class in backend/validation/compliance_checker.py | 2 hours
- Define SR 11-7 requirements checklist and validation logic | 1.5 hours
- Implement compliance scoring and gap analysis | 1.5 hours
Day 4: Document Upload & Processing | 8 hours
- Add document upload endpoint /api/upload-documents to backend/main.py | 1 hour
- Implement file validation and storage for PDF, DOCX, CSV | 1 hour
- Implement PDF text extraction using PyMuPDF | 1 hour
- Implement DOCX text extraction using python-docx | 1 hour
- Add document metadata tracking (type, timestamp, size, format) | 1 hour
- Create DocumentAnalyzer class in backend/validation/document_analyzer.py | 1.5 hours
- Implement model information extraction from documents | 1 hour
- Implement SR 11-7 section detection and gap analysis | 1.5 hours
Day 5: Integration & Backend Testing | 8 hours
- Update ValidationOrchestratorAgent to integrate statistical tests | 1.5 hours
- Wire up model-specific validators into orchestration flow | 1.5 hours
- Integrate compliance checker into validation workflow | 1 hour
- Integrate document analyzer with validation flow | 1 hour
- Add comprehensive error handling and logging | 1 hour
- Write unit tests for new validators | 1.5 hours
- End-to-end backend testing with all model types | 1.5 hours
Day 6: Frontend Enhancements | 8 hours
- Create DocumentUpload component in frontend/src/components/DocumentUpload.jsx | 1.5 hours
- Implement drag-and-drop file upload with multiple file support | 1.5 hours
- Add file type validation, upload progress, and preview | 1 hour
- Add document management UI (list, metadata, delete/replace) | 1 hour
- Integrate document upload with backend API and error handling | 1 hour
- Update ValidationResults component to display new validation metrics | 1.5 hours
- Add basic results display for statistical tests (KS, Gini, PSI, CSI) | 1.5 hours
Day 7: Final Integration, Testing & Documentation | 8 hours
- Complete frontend-backend integration testing | 2 hours
- Test complete flow: upload documents → validate → view results → download report | 2 hours
- Test all model types (Application, Behavioral, Collections Early/Late) | 1.5 hours
- Bug fixes, error handling improvements, and performance optimization | 1.5 hours
- Update API documentation with new endpoints and examples | 0.5 hours
- Create user guide for document upload and validation workflow | 0.5 hours