## Implementation Plan
Task | ETA
Day 1: Project Setup & Architecture | 8 hours
- Initialize project structure (backend/ and frontend/ directories) | 1 hour
- Set up Python virtual environment and install Flask, Flask-CORS | 1 hour
- Install backend dependencies (PyMuPDF, ibm-watson-machine-learning, reportlab, pandas) | 1 hour
- Initialize React project with Vite | 1 hour
- Install frontend dependencies (axios, react-router if needed) | 1 hour
- Create .env.example files for both backend and frontend | 1 hour
- Set up Git repository with proper .gitignore files | 1 hour
- Design API contract and data flow architecture | 1 hour
Day 2: Backend Foundation | 8 hours
- Create Flask app.py with basic server setup | 1 hour
- Implement CORS configuration for frontend communication | 0.5 hours
- Create /api/health endpoint for health checks | 0.5 hours
- Create /api/config endpoint for Watsonx.ai configuration | 1 hour
- Implement file upload handling with validation | 2 hours
- Create utils/ directory and __init__.py | 0.5 hours
- Set up error handling middleware and logging | 1.5 hours
- Test all endpoints with Postman/curl | 1 hour
Day 3: Backend Final Report Generation | 8 hours
- Create utils/final_report.py module | 1 hour
- Implement PDF text extraction using PyMuPDF | 2 hours
- Integrate IBM Watsonx.ai API for final report generation | 2 hours
- Implement PDF generation for final reports using reportlab | 2 hours
- Create /api/generate-final endpoint | 0.5 hours
- Test final report generation end-to-end | 0.5 hours
Day 4: Backend Testing & Refinement | 8 hours
- Write unit tests for backend utilities | 2 hours
- Test complete backend workflow with sample PDFs | 2 hours
- Implement error handling for edge cases | 2 hours
- Add logging and monitoring capabilities | 1 hour
- Performance optimization and code refactoring | 1 hour
Day 5: Frontend Foundation & UI | 8 hours
- Create React app structure (components/, services/, contexts/) | 1 hour
- Build Header component with branding | 1 hour
- Build ConfigPanel component for Watsonx.ai credentials | 1.5 hours
- Create API service layer (services/api.js) for backend calls | 1.5 hours
- Implement global state management for configuration | 1 hour
- Design and implement responsive CSS styling | 1.5 hours
- Test component rendering and basic interactions | 0.5 hours
Day 6: Frontend Forms & Integration | 8 hours
- Build FinalReportForm component with file upload | 2 hours
- Implement drag-and-drop file upload functionality | 1.5 hours
- Add file validation (PDF only, size limits) | 1 hour
- Implement progress indicators and loading states | 1.5 hours
- Add error handling and user feedback messages | 1 hour
- Implement report download functionality | 1 hour
Day 7: Testing, Security & Deployment | 8 hours
- End-to-end testing of complete application workflow | 2 hours
- Security hardening (input validation, API key protection, HTTPS) | 1.5 hours
- Add rate limiting to backend endpoints | 1 hour
- Configure production build (npm run build) | 0.5 hours
- Set up Gunicorn for production Flask deployment | 1 hour
- Create deployment documentation and README | 1 hour
- Final production deployment and smoke testing | 1 hour